## website redevelopment
Website Redevelopment
Manage any type of project. Assign owners, set timelines and keep track of where your project stands.
PPC
Name | Subitems | Owner | Status | Due date | Priority | Timeline - Start | Timeline - End | Item ID (auto generated)
Overview |  | Daniel Conlan | Working on it | 2024-08-29 | High | 2024-08-27 | 2024-08-28 | 1610429011
Templates | Pools - First Draft, Age Groups - First Draft, Locations - First Draft | Daniel Conlan | Working on it | 2024-08-29 | High | 2024-08-30 | 2024-08-30 | 1610481855
Subitems | Name | Owner | Status | Date | Item ID (auto generated)
| Pools - First Draft | Daniel Conlan | Done | 2024-08-29 | 1610488395
| Age Groups - First Draft | Daniel Conlan | Done | 2024-08-29 | 1610488905
| Locations - First Draft | Daniel Conlan | Working on it | 2024-08-29 | 1610489140
|  |  |  | 2024-08-29 |  | 2024-08-27 | 2024-08-30
Learning Portal
Name | Subitems | Owner | Status | Due date | Priority | Timeline - Start | Timeline - End | Item ID (auto generated)
Ideation |  | Daniel Conlan | Not Started | 2024-09-12 | Low | 2024-08-31 | 2024-09-01 | 1610429010
Content Strategy |  |  | Working on it |  | Low |  |  | 1610495746
Design UX/UI |  |  | Not Started |  |  |  |  | 1610503630
CTAs |  |  | Not Started |  |  |  |  | 1610503789
|  |  |  | 2024-09-12 |  | 2024-08-31 | 2024-09-01
Blog
Name | Subitems | Owner | Status | Due date | Priority | Timeline - Start | Timeline - End | Item ID (auto generated)
Migration |  | Daniel Conlan | Not Started |  |  |  |  | 1610494108
Content Audit |  | Daniel Conlan | Working on it | 2024-08-30 | Medium |  |  | 1610494162
Content Strategy |  | Daniel Conlan | Working on it |  | Medium |  |  | 1610495671
Blog Page Design |  |  | Not Started | 2024-09-03 |  |  |  | 1610496750
In-Article Design |  | Daniel Conlan | Done | 2024-09-02 |  |  |  | 1610497017
2024-08-30 to 2024-09-03
Home Page
Name | Subitems | Owner | Status | Due date | Priority | Timeline - Start | Timeline - End | Item ID (auto generated)
Template |  | Daniel Conlan | Not Started |  | Low | 2024-09-19 | 2024-09-19 | 1612350294
[6 empty] | 2024-09-19 | 2024-09-19
Embeds
Name | Subitems | Owner | Status | Due date | Priority | Timeline - Start | Timeline - End | Item ID (auto generated)
CTAs |  |  | Not Started |  |  |  |  | 1610497828
Blog Carousel |  |  | Not Started |  |  |  |  | 1610497956
Childen levels |  | Daniel Conlan | Working on it |  |  |  |  | 1612308934
SEO Optimisation
Name | Subitems | Owner | Status | Due date | Priority | Timeline - Start | Timeline - End | Item ID (auto generated)
On-Page SEO | H1 titles, Meta descriptions, Copy (SEO optimised) | Daniel Conlan | Not Started |  |  |  |  | 1610504405
Subitems | Name | Owner | Status | Date | Item ID (auto generated)
| H1 titles |  |  |  | 1611314626
| Meta descriptions |  |  |  | 1611314725
| Copy (SEO optimised) |  |  |  | 1611315396
Technical SEO |  | Daniel Conlan | Not Started |  |  |  |  | 1610504503
Favicon |  | Daniel Conlan, Shane Webb | Not Started |  |  |  |  | 1610554364
Mobile
Name | Subitems | Owner | Status | Due date | Priority | Timeline - Start | Timeline - End | Item ID (auto generated)
Banner Menu |  |  | Not Started |  |  |  |  | 1610555056
Misc
Name | Subitems | Owner | Status | Due date | Priority | Timeline - Start | Timeline - End | Item ID (auto generated)
Reporting |  |  | Not Started |  |  |  |  | 1612869366
Google Analytics 4 |  | Daniel Conlan, Shane Webb | Not Started | 2024-09-03 |  |  |  | 1612869553
2024-09-03

## website redevelopment-updates
Website Redevelopment | Updates
Item ID | Item Name | Content Type | Content Type | User | Created At | Update Content | Likes Count | Asset IDs | Post ID | Parent Post ID
1610429011 | Overview | Update |  | Daniel Conlan | 28/August/2024 03:22:58 PM | Swimming Nature - PPC | 0 |  | 320959055
1610429011 | Overview | Update |  | Daniel Conlan | 28/August/2024 03:26:27 PM | Context: Many new customers' first touchpoint with the business is searching for terms such as ‘Swimming lessons near me’ and ‘Swimming lessons for kids’ on Google Search. Currently, we pay for sponsored results on these terms, which deliver potential customers to specially-made Unbounce pages. From clicks, to leads, to sales, We currently have Unbounce pages and campaigns for specific pools, age groups, and locations (Dubai). Problem: These Unbounce pages provide a form for contact details and Swimming Nature phone numbers (UK and Dubai). However, users can’t easily find more information about Swimming Nature (course structure, FAQs, etc.) and can’t search for their nearest pool or book lessons right then and there. Currently, we generate approx. 4700 link clicks a month, of which 10% complete the form. Of those, 4% or approximately 20 lead to sales. Solution: Redesign pages on the Swimming Nature website to be suitable for PPC campaigns. Why? >* More functional (search for pools, book lessons) * Better UX/UI for customers * Provide more information Pages to redesign fall into three categories: >* Pools (Bannatyne, Orpington, etc) * Age Groups (Babies, Children, Adults) * Locations (Edinburgh, London, Dubai) | 0 |  | 320960349
1610494162 | Content Audit | Update |  | Daniel Conlan | 29/August/2024 01:17:01 PM | Historical performance | 0 |  | 321291607
1610497017 | In-Article Design | Update |  | Daniel Conlan | 29/August/2024 01:21:15 PM | https://miro.com/app/board/uXjVKBB316g=/?moveToWidget=3458764598417497700&cot=14 | 0 |  | 321293429
1610554364 | Favicon | Update |  | Daniel Conlan | 02/September/2024 07:10:06 AM | The website is currently not.displaying the Favicon on Google. | 0 |  | 321981247
1610554364 | Favicon |  | Reply | Shane Webb | 02/September/2024 07:17:25 AM | This was updated a month ago. I followed their guidelines and Sophia provided update logos. <link rel="icon" href="https://static.swimmingnature.com/skins/sn_web_skins_4.0.6.6/default/styles/rooster/images/favicon.png">It takes time to update, though a month seems long. I could try re-indexing. | 0 |  | 321993567 | 321981247
1610554364 | Favicon |  | Reply | Daniel Conlan | 02/September/2024 08:30:49 AM | Hmmm, not sure exactly what the issue is here. I do think the favicon should be named favicon.ico. I will try indexing the home page via Google Search console. | 0 |  | 322051369 | 321981247
1610554364 | Favicon | Update |  | Daniel Conlan | 02/September/2024 07:11:40 AM |  | 0 | 65676510 | 321981464
1612869553 | Google Analytics 4 | Update |  | Daniel Conlan | 30/August/2024 12:05:29 PM | I don't think we currently have website data running through Google Analytics, or at least I can access it. @Shane Webb Can you have a look? | 0 |  | 321627902
1612869553 | Google Analytics 4 | Update |  | Shane Webb | 01/September/2024 10:30:21 PM | Hi @Daniel Conlan, not sure what is happening with analytics though I can see three accounts for swimmingnature.com, with one of them showing no data. I can see data is coming through. I am not sure whether this is a permission issue, I have added you to the property level access as well. | 0 | 65660801 | 321940803
1612869553 | Google Analytics 4 |  | Reply | Daniel Conlan | 02/September/2024 08:08:10 AM | Thanks will take a look now! | 0 |  | 322030737 | 321940803